## Planning
Week |  | Kilian | Anthony | Jesse | Robert | Faf | Chantal | Comments
# 5 | (Feb 1-5) | Concept Fase
# 6 | (Feb 8-12) | Concept Fase
# 7 | (Feb 15 - 19) | Concept Fase
# 8 | (Feb 22 - 16) | Presetation Concept Fase | [5 empty] | Presetation Wednesday 24th
Full Check & Start Planning Week #10
# 9 | (Feb 29 - Mar 4) | [6 empty] | Holidays
# 10 | (Mar 7 - 11) | 3D_CHAR_001 | 3D_ENEA_001 | 3D_MHOU_001 | 7S_AIBH_001 | 7S_SHLD_001 | 7S_WPSW_001 | <Chantal sick, work delayed>
|  |  | 4U_ENEA_001 | 3D_MHOU_002 |  | 7S_CRHP_001 | 7S_CRCB_001
|  |  | 2D_ENEA_001 | 4U_MHOU_001 |  |  | 7S_WPST_001
4U_MHOU_002
2D_MHOU_001
2D_MHOU_002
3D_MHOU_003
# 11 | (Mar 14 - 18) | 3D_CHAR_001 | 4U_ENEA_001 | 3D_MHOU_003 | 7S_AIBH_001 | 7S_AIHP_001 | 7S_CAMC_001
|  | 4U_CHAR_001 | 2D_ENEA_001 | 4U_MHOU_003 |  |  | 7S_CRCO_001
|  | 2D_CHAR_001 | 5R_ENEA_001 | 2D_MHOU_003
|  |  | 6A_ENEA_001 | 3D_MHOU_004
4U_MHOU_004
2D_MHOU_004
# 12 | (Mar 21 - 25) | 4U_CHAR_001 | 3D_ENWO_001 | 3D_STRL_001 | 7S_ENVI_001 | 7S_CPBH_001 | 7S_RESP_001 | <Fri, Mar 18: no classes>
|  | 2D_CHAR_001 |  | 3D_STRL_002
|  | 5R_CHAR_001 |  | 4U_STRL_001
|  | 6A_CHAR_001 |  | 4U_STRL_002
2D_STRL_002
3D_MBOX_001
4U_MBOX_001
2D_MBOX_001
# 13 | (Mar 28 - Apr 1) | 5R_CHAR_001 | 3D_MBOX_001 | Inplementation | 7S_ENWA_001 | 7S_CPBH_001 | 7S_PICK_001 | <Mon, Mar 28 till Wed, Apr 30: no classes>
|  | 6A_CHAR_001 | 4U_MBOX_001 |  |  |  |  | moved ENWO to dev fase 2,
|  |  | 2D_MBOX_001 |  |  |  |  | moved MBOX & FENC from Jesse to Anthony,
Reason: Saving time for Jesse for Inplementation.
# 14 | (Apr 4 - 8) | 5R_CHAR_001 | 3D_MBOX_001 | Inplementation | 7S_ENWA_001 | 7S_CPBH_001 | Testing Game | moved AIHP from Faf to Chantal,
|  | 6A_CHAR_001 | 4U_MBOX_001 | 3D_ROAD_001 |  |  | 7S_AIHP_001 | Reason: More time for Faf to focus on CPBH &
|  |  | 2D_MBOX_001 | 4U_ROAD_001 |  |  |  | Chantal cant test game yet + other scripts done.
|  |  | 3D_FENC_001 | 2D_ROAD_001
|  |  | 4U_FENC_001 | Scale Fix
2D_FENC_001
3D_ENWO_001
# 15 | (Apr 11 - 15) | 6A_CHAR_001 | 3D_ENWO_001 | Scale Fix |  | 7S_CPBH_001 | Testing Game | <Presetation Dev Fase 1 moved to week #17>
|  | PA_GUNF_001 | 4U_ENWO_001 | 3D_ROAD_002 |  |  | 7S_AIHP_001
|  |  | 2D_ENWO_001 | 4U_ROAD_002 |  |  | 7S_CROS_001
|  |  |  | 2D_ROAD_002 |  |  | Create planning fase2
3D_ROAD_003
4U_ROAD_003
|  |  |  | 2D_ROAD_003 | Inplement Scripts + Testing
# 16 | (Apr 18 - 22) | PA_GUNF_001 | 4U_ENWO_001 | Inplementation | Prezi | 7S_CPBH_001 | Testing Game
|  | PA_ENEH_001 | 2D_ENWO_001 | 2D_ROAD_002
|  | 3D_BRGA_001 | 5R_ENWO_001 | 3D_ROAD_003
|  |  | 6A_ENWO_001 | 4U_ROAD_003
2D_ROAD_003
Inplement Scripts + Testing
|  | Buffer |  |  | Buffer
# 17 | (Apr 25 - 29) | [6 empty] | Tue, Apr 26: Presetation Dev Fase 1
|  | Prepare Presetation |  |  | Prepare Presetation |  |  | <Wed, Apr 27: no classes>
# 18 | (May 2 - 6) | [6 empty] | Holidays
# 19 | (May 9 - 13) | 3D_BRGA_001 | 3D_MINE_001 | 3D_COPA_001 | 7S_AICB_001 | 7S_MINE_001 | 7S_MMAP_001
|  | 4U_BRGA_001 | 4U_MINE_001 | 4U_COPA_001 |  |  | 7S_CRCO_001 | Chantal: Fix dash in CRCO
|  | 2D_BRGA_001 | 2D_MINE_001 | 2D_COPA_001 |  |  |  | COPA deleted > not needed
|  | 3D_RCKE_001 | 3D_NANO_001 | 5R_COPA_001
|  | 4U_RCKE_001 | 4U_NANO_001 | 6A_COPA_001
|  | 2D_RCKE_001 | 2D_NANO_001
# 20 | (May 16 - 20) | 3D_BEWA_001 | 3D_TRUC_001 | 3D_CAR_002 | 7S_BOSF_001 | 7S_NANO_001 | 7S_MMAP_001 | <Mon, May16: no classes>
|  | 4U_BEWA_001 | 4U_TRUC_001 | 4U_CAR_002 |  | 7S_CPCB_001 | 7S_CRCB_001 | Chantal: fix shooting in CRCB
|  | 2D_BEWA_001 | 2D_TRUC_001 | 2D_CAR_002 |  |  |  | NANO deleted > copy of BOSF
|  | 3D_AMPI_001 | 3D_BARE_001 | 3D_OBEN_001 |  |  |  | CPCB week earlier
|  | 4U_AMPI_001 | 4U_BARE_001 | 4U_OBEN_001 |  |  |  | Anthony laptop broken
|  | 2D_AMPI_001 | 2D_BARE_001 | 2D_OBEN_001 |  |  |  | Anthony delayed but no changes needed
|  | 3D_HPPI_001 | 3D_GSPI_001 | 3D_TCAN_001 |  |  |  | Jesse delayed, TCAN to next week
|  | 4U_HPPI_001 | 4U_GSPI_001 | 4U_TCAN_001 |  |  |  | Kilian delayed, RCKE to Anthony
|  | 2D_HPPI_001 | 2D_GSPI_001 | 2D_TCAN_001
|  |  | 3D_RCKE_001 | 6A_COPA_001
4U_RCKE_001
2D_RCKE_001
# 21 | (May 23 - 27) | 3D_CAR_001 | 3D_ELPO_001 | 3D_TREE_001 | 7S_AIPO_001 | 7S_CPCB_001 | 7S_UIME_001 | Anthony delayed but no changes needed
|  | 4U_CAR_001 | 4U_ELPO_001 | 4U_TREE_001 |  |  | 7S_CRCB_001 | CAR_001 Removed > not needed
|  | 2D_CAR_001 | 2D_ELPO_001 | 2D_TREE_001 |  |  |  | Moved TREE to Kilian
|  | 3D_GFLG_001 | 3D_WALL_001 | 3D_LBUI_001
|  | 4U_GFLG_001 | 4U_WALL_001 | 4U_LBUI_001
|  | 2D_GFLG_001 | 2D_WALL_001 | 2D_LBUI_001
|  | 6A_GFLG_001 | 3D_TRLI_001 | Inplement new assets
|  | 3D_TREE_001 | 4U_TRLI_001 | 3D_TCAN_001
|  | 4U_TREE_001 | 2D_TRLI_001 | 4U_TCAN_001
|  | 2D_TREE_001 |  | 2D_TCAN_001
3D_OBEN_001
4U_OBEN_001
2D_OBEN_001
# 22 | (May 30 - Jun 3) | 3D_CPCA_001 | 3D_BWST_001 | 3D_CRAT_001 | 7S_DIFF_001 | 7S_CPCB_001 | 7S_HUDP_001 | TREE + BUSH from assetstore
|  | 4U_CPCA_001 | 4U_BWST_001 | 4U_CRAT_001
|  | 2D_CPCA_001 | 2D_BWST_001 | 2D_CRAT_001
|  | 3D_BUSH_001 | UI_MMEN_001 | 3D_TRSI_001
|  | 4U_BUSH_001 | UI_PMEN_001 | 4U_TRSI_001
|  | 2D_BUSH_001 |  | 2D_TRSI_001
|  | PA_ENEH_001 |  | SN_SHGU_001
|  | PA_ENED_001 |  | SN_SHRO_001
|  | 3D_DSHP_001 |  | SN_SWSW_001
|  | 4U_DSHP_001 |  | Inplementation
2D_DSHP_001
# 23 | (Jun 6 - 10) | PA_EXPL_001 | UI_MMEN_001 | SN_TDMG_001 | 7S_DIFF_001 | 7S_CPCA_001 | 7S_LVLS_001 | Anthony > que 3D assets till laptop fixed
|  | PA_FIRE_001 | UI_PMEN_001 | SN_DDMG_001 | 7S_GMOP_001 | 7S_CPST_001 | 7S_STUP_001 | focusing on 2D assets
|  | PA_SMOK_001 | UI_SWEP_001 | SN_ENWO_001
|  | PA_HPPI_001 | UI_AMMO_001 | SN_ENEA_001
|  | PA_AMPI_001 | UI_CROS_001 | SN_AMBI_001
|  |  | UI_CRED_001 | SN_EXPL_001
SN_MOVE_001
SN_VOIH_001
Inplementation
# 24 | (Jun 13 - 17) | PA_CORE_001 |  | SN_BGMN_001 | 7S_GMOP_001 | 7S_CPST_001 | 7S_STUP_001
|  | PA_DEST_001 |  | SN_BGML_001
|  | PA_ROCF_001 |  | SN_BGMB_001
|  | PA_PYLN_001 |  | SN_BGMD_001
|  | PA_SWGU_001 |  | SN_VOIM_001
PA_ABLA_001
Inplementation
# 25 | (Jun 20 - 24) |  |  |  | Inplementate Scripts & Last Fixes
Prezi presetation
Inplementation
|  | Buffer |  |  | Buffer
# 26 | (Jun 27 - Jul 1) |  |  | Inplementation | Inplementate Scripts & Last Fixes
Discuss presetation
|  | Buffer |  |  | Buffer
# 27 | (Jul 4 - Jul 8) | [6 empty] | Presetation Dev Fase 2

## 3D
Code Name | Full Name | Rig | Animation Code | Animations | Unwrap | Texture | Priority | Time Needed | Time Used | Asset Status | Who | Comments
3D_CHAR_001 | Main Character | 5R_CHAR_001 | 6A_CHAR_001 | Idle | 4U_CHAR_001 | 2D_CHAR_001 | 1 | 50 Hours | 60 Hours | Done | k | Legs, Arms, Cockpit, Weapons
Weapon Switch
Sword Activation
Attack Gun
Attack Rocket
Attack Sword
Walking
Dash
Jump
Dying
3D_COPA_001 | Companion | 5R_COPA_001 | 6A_COPA_001 | Flying | 4U_COPA_001 | 2D_COPA_001 | 2 | 4 Hours | 15 Hours | In Process | j | Drone
Attack
3D_ENWO_001 | Mech Wolf | 5R_ENWO_001 | 6A_ENWO_001 | Idle | 4U_ENWO_001 | 2D_ENWO_001 | 1 | 30 Hours | 30 Hours | Done | a
Walking
Run
Attack
Dying
3D_ENEA_001 | Mech Eagle | 5R_ENEA_001 | 6A_ENEA_001 | Idle | 4U_ENEA_001 | 2D_ENEA_001 | 1 | 25 Hours | 40 Hours | Done | a
Flying
Attack
Dying
3D_ENSP_001 | Mech Spider | 5R_ENSP_001 | 6A_ENSP_001 | Idle | 4U_ENSP_001 | 2D_ENSP_001 | 3 | 20 Hours | x | Scrapped | -
Walking
Attack
Dying
3D_NANO_001 | Nano Power Core | x | x | x | 4U_NANO_001 | 2D_NANO_001 | 1 | 5 Hours | 5 hours | Done | a
3D_SHOU_001 | Small House | x | x | x | 4U_SHOU_001 | 2D_SHOU_001 | 3 | 5 Hours | x | Scrapped | -
3D_SHOU_002 | Small House #2 | x | x | x | 4U_SHOU_002 | 2D_SHOU_002 | 3 | 5 Hours | x | Scrapped | -
3D_SHOU_003 | Small House #3 | x | x | x | 4U_SHOU_003 | 2D_SHOU_003 | 3 | 5 Hours | x | Scrapped | -
3D_MHOU_001 | Medium House | x | x | x | 4U_MHOU_001 | 2D_MHOU_001 | 1 | 10 Hours | 10 Hours | Done | j
3D_MHOU_002 | Medium House #2 | x | x | x | 4U_MHOU_002 | 2D_MHOU_002 | 3 | 10 Hours | 10 Hours | Done | k
3D_MHOU_003 | Medium House #3 | x | x | x | 4U_MHOU_003 | 2D_MHOU_003 | 3 | 10 Hours | 10 Hours | Done | j
3D_MHOU_004 | Medium House #4 | x | x | x | 4U_MHOU_004 | 2D_MHOU_004 | 3 | 10 Hours | 10 Hours | Done | j
3D_LBUI_001 | Large Buildig | x | x | x | 4U_LBUI_001 | 2D_LBUI_001 | 1 | 15 Hours | 5 Hours | In Planning | j
3D_LBUI_002 | Large Buildig #2 | x | x | x | 4U_LBUI_002 | 2D_LBUI_002 | 3 | 15 Hours | x | Scrapped | -
3D_LBUI_003 | Large Buildig #3 | x | x | x | 4U_LBUI_003 | 2D_LBUI_003 | 3 | 15 Hours | x | Scrapped | -
3D_CHAL_001 | City Hall | x | x | x | 4U_CHAL_001 | 2D_CHAL_001 | 1 | 30 Hours | x | Scrapped | - | Boss Room, New boss fight is at Brandenburg
3D_CAR_001 | (Broken) Car | x | x | x | 4U_CAR_001 | 2D_CAR_001 | 2 | 5 Hours | x | Scrapped | -
3D_CAR_002 | (Broken) Car #2 | x | x | x | 4U_CAR_002 | 2D_CAR_002 | 3 | 5 Hours | 5 Hours | Done | j
3D_CAR_003 | (Broken) Car #3 | x | x | x | 4U_CAR_003 | 2D_CAR_003 | 3 | 5 Hours | x | Scrapped | -
3D_TREE_001 | Tree | 5R_TREE_001 | 6A_TREE_001 | Waving Branches | 4U_TREE_001 | 2D_TREE_001 | 2 | 5 Hours |  | In Planning | k
3D_TREE_002 | Tree #2 | 5R_TREE_002 | 6A_TREE_002 | Waving Branches | 4U_TREE_002 | 2D_TREE_002 | 3 | 5 Hours | x | Scrapped | -
3D_TREE_003 | Tree #3 | 5R_TREE_003 | 6A_TREE_003 | Waving Branches | 4U_TREE_003 | 2D_TREE_003 | 3 | 5 Hours | x | Scrapped | -
3D_MINE_001 | Land Mines | x | x | x | 4U_MINE_001 | 2D_MINE_001 | 1 | 2 Hours | 2 Hours | Done | a
3D_HPPI_001 | Health Pickup | x | x | x | 4U_HPPI_001 | 2D_HPPI_001 | 1 | 30 Min | 30 Min | Done | k
3D_CRAT_001 | Crate | x | x | x | 4U_CRAT_001 | 2D_CRAT_001 | 3 | 30 Min |  | In Planning | j
3D_TRUC_001 | (Broken) Truck | x | x | x | 4U_TRUC_001 | 2D_TRUC_001 | 2 | 3 Hours | 3 Hours | Done | a
3D_STRL_001 | Broken Street Light | x | x | x | 4U_STRL_001 | 2D_STRL_001 | 2 | 2 Hours | 2 Hours | Done | j
3D_STRL_002 | Street Light | x | x | x | 4U_STRL_002 | 2D_STRL_002 | 3 | 2 Hours | 2 Hours | Done | j
3D_FENC_001 | Fence | x | x | x | 4U_FENC_001 | 2D_FENC_001 | 2 | 30 Min | 30 Min | Done | a
3D_TCAN_001 | Trash Cans | x | x | x | 4U_TCAN_001 | 2D_TCAN_001 | 2 | 30 Min | 30 Min | Done | j
3D_MBOX_001 | Mail Box | x | x | x | 4U_MBOX_001 | 2D_MBOX_001 | 2 | 30 Min | 30 Min | Done | a
3D_BUSH_001 | Bush | x | x | x | 4U_BUSH_001 | 2D_BUSH_001 | 2 | 30 Min |  | In Planning | k
3D_CSTR_001 | Cracked Streets | x | x | x | 4U_CSTR_001 | 2D_CSTR_001 | 1 | 30 Min |  | Scrapped | -
3D_WALL_001 | Broken Wall | x | x | x | 4U_WALL_001 | 2D_WALL_001 | 2 | 2 Hours |  | In Planning | a
3D_BARE_001 | Barrel | x | x | x | 4U_BARE_001 | 2D_BARE_001 | 3 | 30 Min | 30 Min | Done | a
3D_PLNK_001 | Planks | x | x | x | 4U_PLNK_001 | 2D_PLNK_001 | 3 | 30 Min | x | Scrapped | -
3D_ARCT_001 | Arc De Triomphe | x | x | x | 4U_ARCT_001 | 2D_ARCT_001 | 2 | 20 Hours | x | Scrapped | -
3D_FOUN_001 | Fountain | x | x | x | 4U_FOUN_001 | 2D_FOUN_001 | 3 | 5 Hours | x | Scrapped | -
3D_AMPI_001 | Ammo Pickups | x | x | x | 4U_AMPI_001 | 2D_AMPI_001 | 1 | 30 Min | 30 Min | Done | k
3D_RCKE_001 | Rocket | x | x | x | 4U_RCKE_001 | 2D_RCKE_001 | 2 | 1 Hour | 1 Hour | Done | a
3D_ROUN_001 | Roundabout | x | x | x | 4U_ROUN_001 | 2D_ROUN_001 | 2 | 30 Min | x | Scrapped | -
3D_TRSI_001 | Traffic Signs | x | x | x | 4U_TRSI_001 | 2D_TRSI_001 | 2 | 30 Min |  | In Planning | j | Dirt With Moss
3D_ELPO_001 | Electric Poles | x | x | x | 4U_ELPO_001 | 2D_ELPO_001 | 2 | 30 Min |  | In Planning | a
3D_BRGA_001 | Brandenburg Gate | x | x | x | 4U_BRGA_001 | 2D_BRGA_001 | 3 | 50 Hours | 60 Hours | Done | k
3D_PCEL_001 | Phonecell | x | x | x | 4U_PCEL_001 | 2D_PCEL_001 | 2 | 30 Min | x | Scrapped | -
3D_BWST_001 | Bus Waiting Station | x | x | x | 4U_BWST_001 | 2D_BWST_001 | 2 | 30 Min |  | In Planning | a
3D_BUS_001 | Bus | x | x | x | 4U_BUS_001 | 2D_BUS_001 | 2 | 5 Hours | x | Scrapped | -
3D_GFLG_001 | German Flags | 5R_GFLG_001 | 6A_GFLG_001 | Waving | 4U_GFLG_001 | 2D_GFLG_001 | 2 | 4 Hours | 3 Hours | Done | k
3D_GSPI_001 | German Spire | x | x | x | 4U_GSPI_001 | 2D_GSPI_001 | 3 | 2 Hours | 2 Hours | Done | a | (Pole With Round Thing)
3D_BEWA_001 | Berlin Wall | x | x | x | 4U_BEWA_001 | 2D_BEWA_001 | 3 | 4 Hours | 5 Hours | Done | k
3D_OBEN_001 | Outside Benches | x | x | x | 4U_OBEN_001 | 2D_OBEN_001 | 2 | 2 Hours | 2 Hours | Done | j
3D_IBEN_001 | Inside Benches | x | x | x | 4U_IBEN_001 | 2D_IBEN_001 | 1 | 2 Hours | x | Scrapped | -
3D_COUN_001 | Counter | x | x | x | 4U_COUN_001 | 2D_COUN_001 | 1 | 2 Hours | x | Scrapped | -
3D_TRLI_001 | Traffic Lights | x | x | x | 4U_TRLI_001 | 2D_TRLI_001 | 2 | 30 Min |  | In Planning | a
3D_CPCA_001 | Companion Cannister | x | x | x | 4U_CPCA_001 | 2D_CPCA_001 | 3 | 4 Hours |  | In Planning | k
3D_ROAD_001 | Road (Main) | x | x | x | 4U_ROAD_001 | 2D_ROAD_001 | 1 | 3 Hours | 3 Hours | Done | j
3D_ROAD_002 | Road (Small) | x | x | x | 4U_ROAD_002 | 2D_ROAD_002 | 1 | 3 Hours | 3 Hours | Done | j
3D_ROAD_003 | Road (Main to Small) | x | x | x | 4U_ROAD_003 | 2D_ROAD_003 | 1 | 3 Hours | 3 Hours | Done | j
3D_DSHP_001 | Drop Ship | x | x | x | 4U_DSHP_001 | 2D_DSHP_001 | 1 | 3 Hours |  | In Planning | k | open cube

## UI
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Who | Comments
UI_HP_001 | Health Bar | 1 | 1 Hour
UI_SHLD_001 | Shield | 1 | 1 Hour
UI_MMAP_001 | Mini Map | 1 | 1 Hour | x | Scrapped | - | Scrap reason: its getting pre rendered
UI_SWEP_001 | Selected Weapon | 1 | 1 Hour |  | In Planning | a | Guns, rocket
UI_HPAT_001 | Hexagon Pattern | 1 | 1 Hour
UI_HITD_001 | Hit Detection | 1 | 1 Hour |  |  |  | Blue for hit on shield, Red for hit without shield
UI_AMMO_001 | Ammo | 1 | 1 Hour |  | In Planning | a | bullet + rocket
UI_CROS_001 | Crosshair | 2 | 30 Min |  | In Planning | a | normal, trigger on enemy
UI_MMEN_001 | Main Menu | 1 | 4 Hours |  | In Planning | a | Start screen
UI_PMEN_001 | Pause Menu | 1 | 2 Hours |  | In Planning | a | Pause + Game Options
UI_GOSC_001 | Game Over Screen | 1 | 30 Min
UI_CRED_001 | Credits | 3 | 30 Min |  | In Planning | a
UI_MUTE_001 | Mutter Eliza | 2 | 2 Hours

## Scripts
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Who | Comments
7S_CAMC_001 | Camera Controller | 1 | 1 Week | 3 Weeks | Done | c
7S_CRCO_001 | Character Controller | 1 | 3 Week |  | Done | c | + Dash
7S_SHLD_001 | Character Shield | 1 | 1 Week | 2 Weeks | Done | f
7S_CRHP_001 | Character Health | 1 | 1 Week |  | Done | f
7S_WPSW_001 | Character Weapon Switch | 1 | 1 Week | 1 Week | Done | c
7S_CRCB_001 | Character Combat | 1 | 1 Week |  | In Process | c
7S_WPST_001 | Weapon Stats | 1 | 1 Week | 2 Days | Done | c | Dmg, Range, Ammo
7S_AIBH_001 | AI Behaivor | 1 | 2 Weeks | 2 Weeks | Done | r | Wolf + Eagle
7S_AICB_001 | AI Combat | 1 | 1 Week |  | In Process | r | + E.X.P.
7S_AIHP_001 | AI Health | 1 | 1 Week | 1 Week | Done | f+c
7S_ENWA_001 | Enemy Wave | 1 | 1 Week | 2 Weeks | Done | r
7S_CPBH_001 | Companion Behaivor | 2 | 2 Weeks |  | In Process | f
7S_CPCB_001 | Companion Combat | 2 | 1 Week |  | In Process | f
7S_UIME_001 | UI Menu | 1 | 1 Week | 1 week | Done | c
7S_GMOP_001 | Game Options | 3 | 1 Week |  | In Planning | r
7S_MMAP_001 | Mini Map | 1 | 2 Week | 8 Days | Done | c
7S_RESP_001 | Respawn | 1 | 1 Week | 2 Days | Done | c
7S_MINE_001 | Landmines | 1 | 1 Week |  | Done | f
7S_NANO_001 | Nano Power Core | 1 | 1 Week | x | Scrapped | - | Scrap reason: duplicate from boss fight
7S_ENVI_001 | Environment Interactions | 2 | 1 Week | 1 Week | Done | r
7S_BOSF_001 | Boss Fight | 1 | 1 Week |  | In Planning | r
7S_FOUN_001 | Fountain Water Shader | 3 | 2 Days | x | Scrapped | - | Scrap reason: no fountain asset
7S_HUDP_001 | HUD Popups | 1 | 1 Week |  | In Planning | c
7S_STUP_001 | Stats Upgrades | 3 | 1 Week |  | In Planning | c
7S_LVLS_001 | Level System | 3 | 1 Week |  | In Planning | c
7S_DIFF_001 | Difficulty | 3 | 2 weeks |  | In Planning | r | Medium = Normal, Easy = Weaker, Hard = Stronger, More waves, Less ammo
7S_AIPO_001 | AI Power | 3 | 1 Week |  | In Planning | r | Stats
7S_CPST_001 | Companion Stats | 3 | 1 Week |  | In Planning | f
7S_CPCA_001 | Companion Cannister | 3 | 1 Week |  | In Planning | f
7S_AMMO_001 | Ammo Script | 2 | 3 Days |  | In Planning | c
7S_PICK_001 | Pickup Script | 1 | 1 Week | 4 Days | Done | c
7S_CROS_001 | Crosshair | 3 | 2 Days | 3 Days | Done | c

## Particals
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Who | Comments
PA_FFLY_001 | Flying Flyers | 3 | 2 Hours |  | Scrapped | -
PA_FIRE_001 | Fire | 2 | 2 Hours |  | In Planning | k
PA_DEST_001 | Destruction | 2 | 2 Hours |  | In Planning | k | Break Things
PA_SMOK_001 | Smoke | 2 | 30 Min |  | In Planning | k
PA_GUNF_001 | Gun Fire | 1 | 3 Hours |  | Done | k
PA_EXPL_001 | Explosions | 1 | 1 Hour |  | In Planning | k
PA_ENEH_001 | Enemy Hit | 1 | 1 Hour |  | In Planning | k | Sparks
PA_ENED_001 | Enemy Dead | 2 | 3 Hours |  | In Planning | k | Electric Bolts
PA_CORE_001 | Power Core | 2 | 1 Hour |  | In Planning | k | Glow
PA_PYLN_001 | Pylon | 2 | 1 Hour |  | In Planning | k
PA_HPPI_001 | Health Pickup | 2 | 30 Min |  | In Planning | k
PA_AMPI_001 | Ammo Pickup | 2 | 30 Min |  | In Planning | k
PA_SWGU_001 | Switch Gun | 2 | x |  | - | ~ | Use hit enemy partical
PA_ABLA_001 | Activate Blade | 2 | x |  | - | ~ | Use hit enemy partical
PA_BCAN_001 | Beam Canon | 3 | 3 Hours | x | Scrapped | -
PA_ROCF_001 | Rocket Fire | 2 | 1 Hour |  | In Planning | k
PA_FOUN_001 | Fountain | 2 | ? | x | Scrapped | - | (Internet)

## Sounds
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Who | Comments
SN_MOVE_001 | Moving | 3 | 1 Hour |  | In Planning | j
SN_SHGU_001 | Shooting (Gun) | 1 | 30 Min |  | Done | j
SN_SHRO_001 | Shooting (Rocket) | 1 | 30 Min |  | Done | j
SN_SWSW_001 | Swing Sword | 1 | 30 Min |  | Done | j
SN_TDMG_001 | Taking Damage | 2 | 30 Min |  | In Planning | j
SN_DDMG_001 | Dealing Damage | 2 | 30 Min |  | In Planning | j
SN_ENWO_001 | Enemy Wolf | 2 | 30 Min |  | In Planning | j
SN_ENEA_001 | Enemy Eagle | 2 | 30 Min |  | In Planning | j
SN_ENSP_001 | Enemy Spider | 3 | 30 Min | x | Scrapped | -
SN_AMBI_001 | Ambient Sounds | 1 | 1 Hour |  | In Planning | j
SN_BGMN_001 | Background Music Menu | 2 | 1 Hour |  | In Planning | j
SN_BGML_001 | Background Music Level | 2 | 1 Hour |  | In Planning | j
SN_BGMB_001 | Background Music Boss | 3 | 1 Hour |  | In Planning | j
SN_BGMD_001 | Background Music Dead | 2 | 1 Hour |  | In Planning | j
SN_VOIM_001 | Voice Overs Mutter Eliza | 2 | 3 Hours |  | In Planning | j
SN_VOIH_001 | Voice Overs Hans Bähr | 2 | 3 Hours |  | In Planning | j
SN_EXPL_001 | Explosion | 1 | 30 Min |  | In Planning | j

## Info
Priority |  | Asset Status | Code |  | Planning Status | Week Status
1 = | High |  | 3D = | Model | In Process | Past weeks
2 = | Normal | In Planning | 4U = | Unwrap | Done | Presetation week
3 = | Low | In Procress | 2D = | Texture | Moved | Holiday
|  | Done | 5R = | Rig | Other
|  | Inplemented | 6A = | Animation
|  | Scrapped | UI = | UI Sprites
|  |  | 7S = | Scripts
|  |  | PA = | Particals
|  |  | SN = | Sounds

## Table
| Fase | Robert | Faf | Chan
Dev | Fase 1 | 7S_AIBH_001 | 7S_SHLD_001, 7S_CRHP_001 | 7S_CAMC_001, 7S_CRCO_001
|  | 7S_ENWA_001 | 7S_CPBH_001 | 7S_WPSW_001, 7S_CRCB_001, 7S_WPST_001 | Working on
|  | 7S_ENVI_001 |  | 7S_AIHP_001 | Fase 1/ done
|  |  |  | 7S_RESP_001 | Fase 2/ to do
|  |  |  | 7S_PICK_001 | Extra
7S_CROS_001
| Fase 2 | 7S_AICB_001 | 7S_CPCB_001 | 7S_UIME_001
|  | 7S_GMOP_001 | 7S_MINE_001 | 7S_MMAP_001
|  | 7S_BOSF_001 | 7S_NANO_001 | 7S_HUDP_001
|  | 7S_FOUN_001 | 7S_CPST_001 | 7S_STUP_001
|  | 7S_DIFF_001 | 7S_CPCA_001 | 7S_LVLS_001
7S_AIPO_001
| Fase | Kilian | Anthony | Jesse
Art | Fase 1 | 3D_CHAR_001 | 3D_ENEA_001 | 3D_MHOU_001
|  | 3D_MHOU_002 | 3D_MBOX_001 | 3D_MHOU_003 | Working on
|  | PA_GUNF_001 | 3D_FENC_001 | 3D_MHOU_004 | Fase 1/ done
|  | PA_ENEH_001 | 3D_ENWO_001 | 3D_STRL_001 | Fase 2/ to do
|  | 3D_BRGA_001 |  | 3D_STRL_002 | Extra
3D_ROAD_001
3D_ROAD_002
3D_ROAD_003
| Fase 2 | 3D_BRGA_001 | 3D_NANO_001 | 3D_COPA_001
|  | 3D_CAR_001 | 3D_MINE_001 | 3D_CAR_002
|  | 3D_HPPI_001 | 3D_GSPI_001 | 3D_TREE_001
|  | 3D_AMPI_001 | 3D_TRUC_001 | 3D_TCAN_001
|  | 3D_GFLG_001 | 3D_WALL_001 | 3D_OBEN_001
|  | 3D_CPCA_001 | 3D_BARE_001 | 3D_LBUI_001
|  | 3D_RCKE_001 | 3D_ELPO_001 | 3D_CRAT_001
|  | 3D_BEWA_001 | 3D_TRLI_001 | 3D_BUSH_001
3D_TRSI_001
3D_BWST_001