## Planning
Week |  | Kilian | Anthony | Jesse | Robert | Faf | Chantal | Comments
# 5 | (Feb 1-5) | Concept Fase
# 6 | (Feb 8-12) | Concept Fase
# 7 | (Feb 15 - 19) | Concept Fase
# 8 | (Feb 22 - 16) | Presetation Concept Fase | [5 empty] | Presetation Wednesday 24th
Full Check & Start Planning Week #10
# 9 | (Feb 29 - Mar 4) | [6 empty] | Holidays
# 10 | (Mar 7 - 11) |  |  |  | 7S_AIBH_001 | 7S_SHLD_001 | 7S_WPSW_001
[6 empty] | 7S_CRHP_001 | 7S_CRCB_001
7S_WPST_001
# 11 | (Mar 14 - 18) |  |  |  | 7S_AIBH_001 | 7S_AIHP_001 | 7S_CAMC_001
7S_CRCO_001
# 12 | (Mar 21 - 25) |  |  |  | 7S_ENVI_001 | 7S_CPBH_001 | 7S_RESP_001
# 13 | (Mar 28 - Apr 1) |  |  |  | 7S_ENWA_001 | 7S_CPBH_001 | 7S_PICK_001
# 14 | (Apr 4 - 8) |  |  |  |  | 7S_AICB_001
Inplement Scripts + Testing
# 15 | (Apr 11 - 15) | [6 empty] | Presetation Dev Fase 1
# 16 | (Apr 18 - 22)
# 17 | (Apr 25 - 29)
# 18 | (May 2 - 6) | [6 empty] | Holidays
# 19 | (May 9 - 13)
# 20 | (May 16 - 20)
# 21 | (May 23 - 27)
# 22 | (May 30 - Jun 3)
# 23 | (Jun 6 - 10)
# 24 | (Jun 13 - 17)
# 25 | (Jun 20 - 24)
# 26 | (Jun 27 - Jul 1) | [6 empty] | Presetation Dev Fase 2

## 3D
Code Name | Full Name | Rig | Animation Code | Animations | Unwrap | Texture | Priority | Time Needed | Time Used | Asset Status | Comments
3D_CHAR_001 | Main Character | 5R_CHAR_001 | 6A_CHAR_001 | Idle | 4U_CHAR_001 | 2D_CHAR_001 | 1 | 50 hours |  |  | Legs, Arms, Cockpit, Weapons
Weapon Switch
Sword Activation
Attack Gun
Attack Rocket
Attack Sword
Walking
Dash
Jump
Dying
3D_COPA_001 | Companion | 5R_COPA_001 | 6A_COPA_001 | Flying | 4U_COPA_001 | 2D_COPA_001 | 2 | 4 hours |  |  | Drone
Attack
3D_ENWO_001 | Mech Wolf | 5R_ENWO_001 | 6A_ENWO_001 | Idle | 4U_ENWO_001 | 2D_ENWO_001 | 1 | 30 hours
Walking
Run
Attack
Dying
3D_ENEA_001 | Mech Eagle | 5R_ENEA_001 | 6A_ENEA_001 | Idle | 4U_ENEA_001 | 2D_ENEA_001 | 2 | 25 hours
Flying
Attack
Dying
3D_ENSP_001 | Mech Spider | 5R_ENSP_001 | 6A_ENSP_001 | Idle | 4U_ENSP_001 | 2D_ENSP_001 | 5 | 20 hours
Walking
Attack
Dying
3D_NANO_001 | Nano Power Core | x | x | x | 4U_NANO_001 | 2D_NANO_001 | 1 | 5 hours
3D_SHOU_001 | Small House | x | x | x | 4U_SHOU_001 | 2D_SHOU_001 | 1 | 5 hours
3D_SHOU_002 | Small House #2 | x | x | x | 4U_SHOU_002 | 2D_SHOU_002 | 4 | 5 hours
3D_SHOU_003 | Small House #3 | x | x | x | 4U_SHOU_003 | 2D_SHOU_003 | 5 | 5 hours
3D_MHOU_001 | Medium House | x | x | x | 4U_MHOU_001 | 2D_MHOU_001 | 1 | 10 hours
3D_MHOU_002 | Medium House #2 | x | x | x | 4U_MHOU_002 | 2D_MHOU_002 | 4 | 10 hours
3D_MHOU_003 | Medium House #3 | x | x | x | 4U_MHOU_003 | 2D_MHOU_003 | 5 | 10 hours
3D_LBUI_001 | Large Buildig | x | x | x | 4U_LBUI_001 | 2D_LBUI_001 | 1 | 15 hours
3D_LBUI_002 | Large Buildig #2 | x | x | x | 4U_LBUI_002 | 2D_LBUI_002 | 4 | 15 hours
3D_LBUI_003 | Large Buildig #3 | x | x | x | 4U_LBUI_003 | 2D_LBUI_003 | 5 | 15 hours
3D_CHAL_001 | City Hall | x | x | x | 4U_CHAL_001 | 2D_CHAL_001 | 1 | 30 hours |  |  | Boss Room
3D_CAR_001 | (Broken) Car | x | x | x | 4U_CAR_001 | 2D_CAR_001 | 3 | 5 hours
3D_CAR_002 | (Broken) Car #2 | x | x | x | 4U_CAR_002 | 2D_CAR_002 | 4 | 5 hours
3D_CAR_003 | (Broken) Car #3 | x | x | x | 4U_CAR_003 | 2D_CAR_003 | 4 | 5 hours
3D_TREE_001 | Tree | 5R_TREE_001 | 6A_TREE_001 | Waving Branches | 4U_TREE_001 | 2D_TREE_001 | 2 | 5 hours
3D_TREE_002 | Tree #2 | 5R_TREE_002 | 6A_TREE_002 | Waving Branches | 4U_TREE_002 | 2D_TREE_002 | 5 | 5 hours
3D_TREE_003 | Tree #3 | 5R_TREE_003 | 6A_TREE_003 | Waving Branches | 4U_TREE_003 | 2D_TREE_003 | 5 | 5 hours
3D_MINE_001 | Land Mines | x | x | x | 4U_MINE_001 | 2D_MINE_001 | 1 | 2 hours
3D_HPPI_001 | Health Pickup | x | x | x | 4U_HPPI_001 | 2D_HPPI_001 | 2 | 30 min
3D_CRAT_001 | Crates | x | x | x | 4U_CRAT_001 | 2D_CRAT_001 | 4 | 30 min
3D_TRUC_001 | (Broken) Truck | x | x | x | 4U_TRUC_001 | 2D_TRUC_001 | 5 | 3 hours
3D_STRL_001 | Broken Street Light | x | x | x | 4U_STRL_001 | 2D_STRL_001 | 4 | 2 hours
3D_FENC_001 | Fence | x | x | x | 4U_FENC_001 | 2D_FENC_001 | 3 | 30 min
3D_TCAN_001 | Trash Cans | x | x | x | 4U_TCAN_001 | 2D_TCAN_001 | 5 | 30 min
3D_MBOX_001 | Mail Box | x | x | x | 4U_MBOX_001 | 2D_MBOX_001 | 3 | 30 min
3D_BUCH_001 | Bushes | x | x | x | 4U_BUCH_001 | 2D_BUCH_001 | 2 | 30 min
3D_CSTR_001 | Cracked Streets | x | x | x | 4U_CSTR_001 | 2D_CSTR_001 | 1 | 30min
3D_WALL_001 | Broken Walls | x | x | x | 4U_WALL_001 | 2D_WALL_001 | 3 | 2 hours
3D_BARE_001 | Barrels | x | x | x | 4U_BARE_001 | 2D_BARE_001 | 5 | 30 min
3D_PLNK_001 | Planks | x | x | x | 4U_PLNK_001 | 2D_PLNK_001 | 4 | 30min
3D_ARCT_001 | Arc De Triomphe | x | x | x | 4U_ARCT_001 | 2D_ARCT_001 | 2 | 20 hours
3D_FOUN_001 | Fountain | x | x | x | 4U_FOUN_001 | 2D_FOUN_001 | 3 | 5 hours
3D_AMPI_001 | Ammo Pickups | x | x | x | 4U_AMPI_001 | 2D_AMPI_001 | 1 | 3 hours
3D_RCKE_001 | Rocket | x | x | x | 4U_RCKE_001 | 2D_RCKE_001 | 2 | 1 hour
3D_ROUN_001 | Roundabout | x | x | x | 4U_ROUN_001 | 2D_ROUN_001 | 3 | 30 min
3D_TRSI_001 | Traffic Signs | x | x | x | 4U_TRSI_001 | 2D_TRSI_001 | 3 | 30 min |  |  | Dirt With Moss
3D_ELPO_001 | Electric Poles | x | x | x | 4U_ELPO_001 | 2D_ELPO_001 | 5 | 30 min
3D_BRGA_001 | Brandenburg Gate | x | x | x | 4U_BRGA_001 | 2D_BRGA_001 | 5 | 50 hours
3D_PCEL_001 | Phonecell | x | x | x | 4U_PCEL_001 | 2D_PCEL_001 | 3 | 30min
3D_BWST_001 | Bus Waiting Station | x | x | x | 4U_BWST_001 | 2D_BWST_001 | 3 | 30min
3D_BUS_001 | Bus | x | x | x | 4U_BUS_001 | 2D_BUS_001 | 3 | 5 hours
3D_GFLG_001 | German Flags | 5R_GFLG_001 | 6A_GFLG_001 | Waving | 4U_GFLG_001 | 2D_GFLG_001 | 2 | 4 hours
3D_GSPI_001 | German Spire | x | x | x | 4U_GSPI_001 | 2D_GSPI_001 | 3 | 2 hours |  |  | (Pole With Round Thing)
3D_BEWA_001 | Berlin Wall | x | x | x | 4U_BEWA_001 | 2D_BEWA_001 | 3 | 4 hours
3D_OBEN_001 | Outside Benches | x | x | x | 4U_OBEN_001 | 2D_OBEN_001 | 3 | 2 hours
3D_IBEN_001 | Inside Benches | x | x | x | 4U_IBEN_001 | 2D_IBEN_001 | 3 | 2 hours
3D_COUN_001 | Counter | x | x | x | 4U_COUN_001 | 2D_COUN_001 | 2 | 2 hours
3D_TRLI_001 | Traffic Lights | x | x | x | 4U_TRLI_001 | 2D_TRLI_001 | 3 | 30 min
3D_CPCA_001 | Companion Cannister | x | x | x | 4U_CPCA_001 | 2D_CPCA_001 | 5 | 4 hours

## UI
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Comments
UI_HP_001 | Health Bar | 1 | 1 hour
UI_SHLD_001 | Shield | 1 | 1 hour
UI_MMAP_001 | Mini Map | 1 | 1 hour
UI_SWEP_001 | Selected Weapon | 1 | 1 hour
UI_HPAT_001 | Hexagon Pattern | 1 | 1 hour
UI_HITD_001 | Hit Detection | 1 | 1 hour |  |  | Blue for hit on shield, Red for hit without shield
UI_AMMO_001 | Ammo | 1 | 1 hour
UI_CROS_001 | Crosshair | 2 | 30 min
UI_MMEN_001 | Main Menu | 1 | 4 hours
UI_PMEN_001 | Pause Menu | 1 | 2 hours
UI_GOSC_001 | Game Over Screen | 1 | 30 min
UI_CRED_001 | Credits | 3 | 30 min
UI_MUTE_001 | Mutter Eliza | 2 | 2 hours

## Scripts
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Comments
7S_CAMC_001 | Camera Controller | 1 | 1 Week |  | In Planning
7S_CRCO_001 | Character Controller | 1 | 3 Week |  | In Planning | + Dash
7S_SHLD_001 | Character Shield | 1 | 1 Week |  | In Planning
7S_CRHP_001 | Character Health | 1 | 1 Week |  | In Planning
7S_WPSW_001 | Character Weapon Switch | 1 | 1 Week |  | In Planning
7S_CRCB_001 | Character Combat | 1 | 1 Week |  | In Planning
7S_WPST_001 | Weapon Stats | 1 | 1 Week |  | In Planning | Dmg, Range, Ammo
7S_AIBH_001 | AI Behaivor | 1 | 2 Weeks |  | In Planning | Wolf + Eagle
7S_AICB_001 | AI Combat | 1 | 1 Week |  | In Planning | + E.X.P.
7S_AIHP_001 | AI Health | 1 | 1 Week |  | In Planning
7S_ENWA_001 | Enemy Wave | 2 | 1 Week |  | In Planning
7S_CPBH_001 | Companion Behaivor | 2 | 2 Weeks |  | In Planning
7S_CPCB_001 | Companion Combat | 2 | 1 Week
7S_UIME_001 | UI Menu | 1 | 1 Week
7S_GMOP_001 | Game Options | 4 | 1 week
7S_MMAP_001 | Mini Map | 2 | 2 Week
7S_RESP_001 | Respawn | 1 | 1 Week |  | In Planning
7S_MINE_001 | Landmines | 1 | 1 Week
7S_NANO_001 | Nano Power Core | 1 | 1 Week
7S_ENVI_001 | Environment Interactions | 2 | 1 Week |  | In Planning
7S_BOSF_001 | Boss Fight | 1 | 1 Week
7S_FOUN_001 | Fountain Water Shader | 3 | 2 Days
7S_HUDP_001 | HUD Popups | 1 | 1 Week
7S_STUP_001 | Stats Upgrades | 5 | 1 Week
7S_LVLS_001 | Level System | 5 | 1 Week
7S_DIFF_001 | Difficulty | 5 | 2 weeks |  |  | Medium = Normal, Easy = Weaker, Hard = Stronger, More waves, Less ammo
7S_AIPO_001 | AI Power | 4 | 1 Week |  |  | Stats
7S_CPST_001 | Companion Stats | 5 | 1 Week
7S_CPCA_001 | Companion Cannister | 5 | 1 Week
7S_AMMO_001 | Ammo Script | 3 | 3 Days
7S_PICK_001 | Pickup Script | 2 | 1 Week |  | In Planning

## Particals
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Comments
PA_FFLY_001 | Flying Flyers | 4 | 2 hours
PA_FIRE_001 | Fire | 2 | 2 hours
PA_DEST_001 | Destruction | 2 | 2 hours |  |  | Break Things
PA_SMOK_001 | Smoke | 2 | 30 min
PA_GUNF_001 | Gun Fire | 1 | 3 hours
PA_EXPL_001 | Explosions | 1 | 1 hour
PA_ENEH_001 | Enemy Hit | 1 | 1 hour |  |  | Sparks
PA_ENED_001 | Enemy Dead | 2 | 3 hours |  |  | Electric Bolts
PA_CORE_001 | Power Core | 2 | 1 hour |  |  | Glow
PA_PYLN_001 | Pylon | 2 | 1 hour
PA_HPPI_001 | Health Pickup | 2 | 30 min
PA_AMPI_001 | Ammo Pickup | 2 | 30 min
PA_SWGU_001 | Switch Gun | 3 | x |  |  | Use hit enemy partical
PA_ABLA_001 | Activate Blade | 3 | x |  |  | Use hit enemy partical
PA_BCAN_001 | Beam Canon | 5 | 3 hours
PA_ROCF_001 | Rocket Fire | 3 | 1 hour
PA_FOUN_001 | Fountain | 3 | ? |  |  | (Internet)

## Sounds
Code Name | Full Name | Priority | Time Needed | Time Used | Asset Status | Comments
SN_MOVE_001 | Moving | 4 | 1 hour
SN_SHGU_001 | Shooting (Gun) | 1 | 30 min
SN_SHRO_001 | Shooting (Rocket) | 1 | 30 min
SN_SWSW_001 | Swing Sword | 1 | 30min
SN_TDMG_001 | Taking Damage | 2 | 30min
SN_DDMG_001 | Dealing Damage | 2 | 30 min
SN_ENWO_001 | Enemy Wolf | 3 | 30 min
SN_ENEA_001 | Enemy Eagle | 3 | 30 min
SN_ENSP_001 | Enemy Spider | 5 | 30 min
SN_AMBI_001 | Ambient Sounds | 2 | 1 hour
SN_BGMN_001 | Background Music Menu | 2 | 1 hour
SN_BGML_001 | Background Music Level | 2 | 1 hour
SN_BGMB_001 | Background Music Boss | 2 | 1 hour
SN_BGMD_001 | Background Music Dead | 2 | 1 hour
SN_VOIM_001 | Voice Overs Mutter Eliza | 3 | 3 hours
SN_VOIH_001 | Voice Overs Hans Bähr | 3 | 3 hours
SN_EXPL_001 | Explosion | 1 | 30 min

## Info
Priority |  | Asset Status |  | Code
1 = | Very High |  |  | 3D = | Model
2 = | High |  | In Planning | 4U = | Unwrap
3 = | Normal |  | In Procress | 2D = | Texture
4 = | Low |  | Done | 5R = | Rig
5 = | Very Low |  | Inplemented | 6A = | Animation
|  |  | Scrapped | UI = | UI Sprites
|  |  |  | 7S = | Scripts
|  |  |  | PA = | Particals
|  |  |  | SN = | Sounds