## Planning
Week |  | Kilian | Anthony | Jesse | Robert | Faf | Chantal | Comments
# 5 | (Feb 1-5) | Concept Fase
# 6 | (Feb 8-12) | Concept Fase
# 7 | (Feb 15 - 19) | Concept Fase
# 8 | (Feb 22 - 16) | Presetation Concept Fase | [5 empty] | Presetation Wednesday 24th
# 9 | (Feb 29 - Mar 4) | [6 empty] | Vakantie
# 10 | (Mar 7 - 11)
# 11 | (Mar 14 - 18)
# 12 | (Mar 21 - 25)
# 13 | (Mar 28 - Apr 1)
# 14 | (Apr 4 - 8)
# 15 | (Apr 11 - 15) | [6 empty] | Presetation Dev Fase 1
# 16 | (Apr 18 - 22)
# 17 | (Apr 25 - 29)
# 18 | (May 2 - 6) | [6 empty] | Vakantie
# 19 | (May 9 - 13)
# 20 | (May 16 - 20)
# 21 | (May 23 - 27)
# 22 | (May 30 - Jun 3)
# 23 | (Jun 6 - 10)
# 24 | (Jun 13 - 17)
# 25 | (Jun 20 - 24)
# 26 | (Jun 27 - Jul 1) | [6 empty] | Presetation Dev Fase 2

## 3D
Code Name | Full Name | Rig | Animation Code | Animations | Texture | Priority | Time Needed | Time Used | In planning | Comments
| Main Character |  |  | Idle |  | 1 | 50 hours |  |  | Legs, Arms, Cockpit, Weapons
Weapon Switch
Sword Activation
Attack Gun
Attack Rocket
Attack Sword
Walking
Dash
Jump
Dying
| Companion |  |  | Flying |  | 2 | 4 hours |  |  | Drone
Attack
| Mech Wolf |  |  | Idle |  | 1 | 30 hours
Walking
Run
Attack
Dying
| Mech Eagle |  |  | Idle |  | 2 | 25 hours
Flying
Attack
Dying
| Mech Spider |  |  | Idle |  | 5 | 20 hours
Walking
Attack
Dying
| Nano Power Core | x | x | x |  | 1 | 5 hours
| Small Houses | x | x | x |  | 1 | 5 hours
| Medium Houses | x | x | x |  | 1 | 10 hours
| Large Buildigs | x | x | x |  | 1 | 15 hours
| City Hall | x | x | x |  | 1 | 30 hours
| (Broken) Cars | x | x | x |  | 3 | 5 hours
| Trees |  |  | Waving Branches |  | 2 | 5 hours
| Land Mines | x | x | x |  | 1 | 2 hours
| Health Pickup | x | x | x |  | 2 | 30 min
| Crates | x | x | x |  | 4 | 30 min
| (Broken) Truck | x | x | x |  | 5 | 3 hours
| Broken Street Light | x | x | x |  | 4 | 2 hours
| Fence | x | x | x |  | 3 | 30 min
| Trash Cans | x | x | x |  | 5 | 30 min
| Mail Box | x | x | x |  | 3 | 30 min
| Bushes | x | x | x |  | 2 | 30 min
| Cracked Streets | x | x | x |  | 1 | 30min
| Broken Walls | x | x | x |  | 3 | 2 hours
| Barrels | x | x | x |  | 5 | 30 min
| Planks | x | x | x |  | 4 | 30min
| Arc De Triomphe | x | x | x |  | 2 | 20 hours
| Fountain | x | x | x |  | 3 | 5 hours
| Ammo Pickups | x | x | x |  | 1 | 3 hours
| Rocket | x | x | x |  | 2 | 1 hour
| Roundabout | x | x | x |  | 3 | 30 min
| Traffic Signs | x | x | x |  | 3 | 30 min |  |  | Dirt With Moss
| Electric Poles | x | x | x |  | 5 | 30 min
| Brandenburg Gate | x | x | x |  | 5 | 50 hours
| Phonecell | x | x | x |  | 3 | 30min
| Bus Waiting Station | x | x | x |  | 3 | 30min
| Bus | x | x | x |  | 3 | 5 hours
| German Flags |  |  | Waving |  | 2 | 4 hours
| German Spire | x | x | x |  | 3 | 2 hours |  |  | (Pole With Round Thing)
| Berlin Wall | x | x | x |  | 3 | 4 hours
| Outside Benches | x | x | x |  | 3 | 2 hours
| Inside Benches | x | x | x |  | 3 | 2 hours
| Counter | x | x | x |  | 2 | 2 hours
| Traffic Lights | x | x | x |  | 3 | 30 min

## UI
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
| Health Bar | 1 | 1 hour
| Shield | 1 | 1 hour
| Mini Map | 1 | 1 hour
| Selected Weapon | 1 | 1 hour
| Hexagon Pattern | 1 | 1 hour
| Hit Detection | 1 | 1 hour |  |  | Blue for hit on shield, Red for hit without shield
| Ammo | 1 | 1 hour
| Crosshair | 2 | 30 min
| Main Menu | 1 | 4 hours
| Pause Menu | 1 | 2 hours
| Game Over Screen | 1 | 30 min
| Credits | 3 | 30 min
| Mutter Eliza | 2 | 2 hours

## Scripts
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
Character Controller
Character Health
Weapon Switch
Character Attack
AI
Mini Map

## Particals
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
| Flying Flyers | 4 | 2 hours
| Fire | 2 | 2 hours
| Destruction | 2 | 2 hours |  |  | Break Things
| Smoke | 2 | 30 min
| Gun Fire | 1 | 3 hours
| Explosions | 1 | 1 hour
| Hit Enemy | 1 | 1 hour |  |  | Sparks
| Enemy Dead | 2 | 3 hours |  |  | Electric Bolts
| Power Core | 2 | 1 hour |  |  | Glow
| Pylon | 2 | 1 hour
| Health Pickup | 2 | 30 min
| Ammo Pickup | 2 | 30 min
| Gun Switch | 3 | x |  |  | Use hit enemy partical
| Activate Blade | 3 | x |  |  | Use hit enemy partical
| Beam Canon | 5 | 3 hours
| Rocket Fire | 3 | 1 hour
| Fountain | 3 |  |  |  | (Internet)

## Sounds
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
Moving
Shooting (Gun)
Shooting (Rocket)
Swing Sword
Taking Damage
Dealing Damage
Enemy Wolf
Enemy Eagle
Enemy Spider
Ambient Sounds
Background Noises
Voice Overs
Explosion

## Info
Priority |  | Asset Status
1 = | Very High
2 = | High |  | In Procress
3 = | Normal |  | Done
4 = | Low |  | Inplemented
5 = | Very Low |  | Scrapped