## Planning
Week |  | Kilian | Anthony | Jesse | Robert | Faf | Chantal | Comments
# 5 | (Feb 1-5) | Concept Fase
# 6 | (Feb 8-12) | Concept Fase
# 7 | (Feb 15 - 19) | Concept Fase
# 8 | (Feb 22 - 16) | Presetation Concept Fase | [5 empty] | Presetation Wednesday 24th
# 9 | (Feb 29 - Mar 4) | [6 empty] | Vakantie
# 10 | (Mar 7 - 11)
# 11 | (Mar 14 - 18)
# 12 | (Mar 21 - 25)
# 13 | (Mar 28 - Apr 1)
# 14 | (Apr 4 - 8)
# 15 | (Apr 11 - 15) | [6 empty] | Presetation Dev Fase 1
# 16 | (Apr 18 - 22)
# 17 | (Apr 25 - 29)
# 18 | (May 2 - 6) | [6 empty] | Vakantie
# 19 | (May 9 - 13)
# 20 | (May 16 - 20)
# 21 | (May 23 - 27)
# 22 | (May 30 - Jun 3)
# 23 | (Jun 6 - 10)
# 24 | (Jun 13 - 17)
# 25 | (Jun 20 - 24)
# 26 | (Jun 27 - Jul 1) | [6 empty] | Presetation Dev Fase 2

## 3D
Code Name | Full Name | Rig | Animations | Texture | Priority | Time Needed | Time Used | In planning | Comments
| Main Character | yes | weapon switch |  | 1 | 40 hours |  |  | Legs, Arms, cockpit, wapens
idle
attack
walk
boost
dead
jump
| companion | yes | fly |  | 2 | 4 hours |  |  | drone
attack
| mech wolf | yes | walking |  | 1 | 30 hours
run
attack
dead
idle
| Mech Eagle | yes | idle |  | 2 | 25 hours
fly
attack
dead
| Mech Spider | yes | idle |  | 5 | 20 hours
walking
attack
dead
| nano power core | x | x |  | 1 | 5 hours
| small houses | x | x |  | 1 | 5 hours
| medium houses | x | x |  | 1 | 10 hours
| large buildigs | x | x |  | 1 | 15 hours
| city hall | x | x |  | 1 | 30 hours
| (broken) cars | x | x |  | 3 | 5 hours
| trees |  |  |  | 2 | 5 hours
| land mines | x | x |  | 1 | 2 hours
| health pickup | x | x |  | 2 | 30 min
| crates | x | x |  | 4 | 30 min
| (broken) truck | x | x |  | 5 | 3 hours
| broken street light | x | x |  | 4 | 2 hours
| fence | x | x |  | 3 | 30 min
| trash cans | x | x |  | 5 | 30 min
| mail box | x | x |  | 3 | 30 min
| bushes | x | x |  | 2 | 30 min
| cracked streets | x | x |  | 1 | 30min
| broken walls | x | x |  | 3 | 2 hours
| barrels | x | x |  | 5 | 30 min
| planks | x | x |  | 4 | 30min
| arc de triomphe | x | x |  | 2 | 20 hours
| fountain | x | x |  | 3 | 5 hours
| ammo pickups | x | x |  | 1 | 3 hours
| rocket | x | x |  | 2 | 1 hour
| roundabout | x | x |  | 3 | 30 min
| traffic signs | x | x |  | 3 | 30 min |  |  | dirt with moss
| electric poles | x | x |  | 5 | 30 min
| brandenburg gate | x | x |  | 5 | 50 hours
| phonecell | x | x |  | 3 | 30min
| bus waiting station | x | x |  | 3 | 30min
| bus | x | x |  | 3 | 5 hours
| german flags | yes | waving |  | 2 | 4 hours
| german spire | x | x |  | 3 | 2 hours |  |  | (pole with round thing)
| berlin wall | x | x |  | 3 | 4 hours
| outside benches | x | x |  | 3 | 2 hours
| inside benches | x | x |  | 3 | 2 hours
| counter | x | x |  | 2 | 2 hours
| traffic lights | x | x |  | 3 | 30 min

## 2D
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
| health bar | 1 | 1 hour
| shield | 1 | 1 hour
| minimap | 1 | 1 hour
| selected weapon | 1 | 1 hour
| hexagon pattern | 1 | 1 hour
| hit detection | 1 | 1 hour |  |  | blue for hit on shield, red for hit without shield
| ammo | 1 | 1 hour
| crosshair | 2 | 30 min
| main menu | 1 | 4 hours
| pause menu | 1 | 2 hours
| game over screen | 1 | 30 min
| credits | 3 | 30 min
| Mutter Eliza | 2 | 2 hours

## Scripts
Code Name | Full Name | Purpose | Priority | Time Needed | Time Used | In planning | Comments

## Particals
Code Name | Full Name | Purpose | Priority | Time Needed | Time Used | In planning | Comments
| flying flyers |  | 4 | 2 hours
| fire |  | 2 | 2 hours
| destruction |  | 2 | 2 hours |  |  | break things
| smoke |  | 2 | 30 min
| gun fire |  | 1 | 3 hours
| explosions |  | 1 | 1 hour
| hit enemy |  | 1 | 1 hour |  |  | sparks
| enemy dead |  | 2 | 3 hours |  |  | electric bolts
| power core |  | 2 | 1 hour |  |  | glow
| pylon |  | 2 | 1 hour
| health pickup |  | 2 | 30 min
| ammo pickup |  | 2 | 30 min
| gun switch |  | 3 | x |  |  | use hit enemy partical
| activate blade |  | 3 | x |  |  | use hit enemy partical
| beam canon |  | 5 | 3 hours
| rocket fire |  | 3 | 1 hour
| fountain |  | 3 |  |  |  | internet

## Sounds
Code Name | Full Name | Priority | Time Needed | Time Used | In planning | Comments
moving
shooting (gun)
shooting (rocket)
swinging melee
taking damage
dealing damage
Enemy wolf
enemy eagle
Enemy Spider
Ambient sounds
background noises
voice overs
explosion